## Sheet1
CONTINGENCY PLANNING
No. | Type of contingency reviewed | Current status | Action plan | Who is Responsible | Target Date | Status
1 | The Apelo Dental Clinic Management System (ADENICSY) would not synchronize the data/information of the patient being recorded if the internet connection is disrupted and/or lost during the process. | To Be Done | Create a local storage backup from time to time in the clinic's computer which the system can use and update for the business transactions, when the internet is restored, the changes will be synced to the cloud server. | Development Team | 1-2 Weeks | Have a local storage back up in the clinic's computer/s that can be saved and used to restore whem the internet connection is restored
2 | The information cannot be transferred/exchanged safely if the internet connection is lost and if there was a problem/issue that unexpectedly occurs with the router that connects the devices together.
3 | The data in the Apelo Dental Clinic Management System (ADENICSY) can be vulnerable with risks when it comes to new employees being hired since the core data, which is the patient’s recorded data, can be interacted by the employees. | To Be Done When Deployed and Currently Used by Client | Once the team teaches/trains the Staff of the Clinic on how the system functions, the Staff should be able to relay the knowledge and teach/train possible new employees to properly and safely use the system. | Clinic Staff (For training new employees of the clinic) Development Team (For training the Clinic Staff on how the System functions) | 1 Week | Successfully taught the Staff the functions of the System
4 | The system may not work well with current hardware and software systems, which could lead to errors and delays in the system. | In Progress | Optimize the system and make sure it is compatible to work on current hardware. | Development Team | 1-2 Weeks | Optimized enough to be compatible with the current hardware
5 | There is a chance that there won't be enough resources available to finish the project on schedule, which will cause delays and cost overruns. | In Progress | Develop as much as the team can, and present the requested working functions of the system. | Development Team | 2-3 Weeks | Working and Necessary Functions are successfully developed
6 | Data breaches and cyberattacks pose a threat that could compromise sensitive data. | To Be Done | Ensure that the computer in the clinic that is used to access the website has an anti-virus, and is not used to access random websites that could potentially harm the user and gain access to the sensitive information | Development Team (Checking of the device if it has malicious activity and/or contains potentially harmful viruses) Staff (Ensuring that the computer/s in the clinic are kept safe and out of access from strangers/non-staff members) | 1 Weeks | Confirm that the computer in the clinic does not contain malicious files and is primarily used for Clinic purposes.
7 | Certain functions of the system may have a error or does not respond accordingly | In Progress | Double checking of functions in the system to make sure they work properly and accordingly. | Development Team | 1-2 Weeks | Lessened to the best of the team's ability
PREPARED BY: CHECKED BY: APPROVED BY: